## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 |  | US-01 | As a product researcher, I want to define a product, audience and research objective so I can set up an experiment. | Must | — |  | Planned
2 |  | US-02 | As a researcher, I want the system to generate diverse persona profiles so I can explore different user viewpoints. | Must | US-01 |  | Planned
2 |  | US-03 | As a researcher, I want personas to keep their traits and past context so their answers stay consistent. | Must | US-02 |  | Planned
3 |  | US-04 | As a researcher, I want all selected personas to answer a survey so I can compare their responses. | Must | US-01, US-02 |  | Planned
4 |  | US-05 | As a researcher, I want to interview one persona over multiple turns so I can explore its views in more detail. | Must | US-02, US-03 |  | Planned
4 |  | US-06 | As a researcher, I want key themes, sentiment and behavior patterns summarized from responses. | Must | US-04, US-05 |  | Planned
4 |  | US-07 | As a researcher, I want a “Would use this product?” score by persona group with a short reason. | Should | US-04, US-06 |  | Planned
5 |  | US-08 | As a researcher, I want to see themes, sentiment, quotes and validation scores in a results dashboard. | Must | US-06, US-07 |  | Planned
5 |  | US-09 | As a researcher, I want to download a PDF report with personas, response highlights and findings. | Must | US-06, US-07 |  | Planned
6 |  | US-10 | As a researcher, I want the complete experiment flow checked from setup through report download. | Must | US-02 to US-09 |  | Planned
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG — PLANNED
US-01 | 1 | Review the project goal and target users | 2026-08-03 12:00 | 2026-08-03 12:00 |  | Planning | Planned | 2
US-01 | 2 | Study synthetic-user research and persona simulation | 2026-08-04 12:00 | 2026-08-04 12:00 |  | Planning | Planned | 2
US-01 | 3 | Write the product, audience and research objective | 2026-08-05 12:00 | 2026-08-05 12:00 |  | Planning | Planned | 2
US-01 | 4 | List the main experiment steps | 2026-08-06 12:00 | 2026-08-06 12:00 |  | Planning | Planned | 2
US-01 | 5 | Draft the system architecture | 2026-08-07 12:00 | 2026-08-07 12:00 |  | Planning | Planned | 2
US-01 | 1900-01-05 | Define persona fields and attributes | 46244.5 | 2026-08-10 12:00 |  | Planning | Planned | 2
US-01 | 1900-01-06 | Outline the persona generation agent | 46245.5 | 2026-08-11 12:00 |  | Planning | Planned | 2
US-01 | 1900-01-07 | Sketch the research workspace | 46246.5 | 2026-08-12 12:00 |  | Planning | Planned | 2
US-01 | 1900-01-08 | Review milestone 1 learning topics | 46247.5 | 2026-08-13 12:00 |  | Planning | Planned | 2
US-01 | 1900-01-09 | Summarize open design questions | 46248.5 | 2026-08-14 12:00 |  | Planning | Planned | 2
SPRINT 2 BACKLOG — PLANNED
US-01 | 1899-12-31 | Refine the system architecture | 46251.5 | 2026-08-17 12:00 |  | Planning | Planned | 2
US-01 | 1900-01-01 | Define agent roles and responsibilities | 46252.5 | 2026-08-18 12:00 |  | Planning | Planned | 2
US-01 | 1900-01-02 | Design the persona data model | 46253.5 | 2026-08-19 12:00 |  | Planning | Planned | 2
US-01 | 1900-01-03 | Plan the experiment workflow | 46254.5 | 2026-08-20 12:00 |  | Planning | Planned | 2
US-01 | 1900-01-04 | Plan the research workspace fields | 46255.5 | 2026-08-21 12:00 |  | Planning | Planned | 2
US-01 | 1900-01-05 | Prepare persona card content | 46258.5 | 2026-08-24 12:00 |  | Planning | Planned | 2
US-01 | 1900-01-06 | Review persona diversity requirements | 46259.5 | 2026-08-25 12:00 |  | Planning | Planned | 2
US-01 | 1900-01-07 | Study LLM grounding and context limits | 46260.5 | 2026-08-26 12:00 |  | Planning | Planned | 2
US-01 | 1900-01-08 | Document risks and assumptions | 46261.5 | 2026-08-27 12:00 |  | Planning | Planned | 2
US-01 | 1900-01-09 | Prepare milestone 2 design notes | 46262.5 | 2026-08-28 12:00 |  | Planning | Planned | 2
SPRINT 3 BACKLOG — PLANNED
US-02 | 1 | Plan persona generation inputs | 2026-08-31 12:00 | 2026-08-31 12:00 |  | Planning | Planned | 2
US-02 | 2 | Define persona name, age and occupation fields | 2026-09-01 12:00 | 2026-09-01 12:00 |  | Planning | Planned | 2
US-02 | 3 | Define personality and behavior fields | 2026-09-02 12:00 | 2026-09-02 12:00 |  | Planning | Planned | 2
US-02 | 4 | Draft persona generation prompt requirements | 2026-09-03 12:00 | 2026-09-03 12:00 |  | Planning | Planned | 2
US-02 | 5 | Plan persona cards for the workspace | 2026-09-07 12:00 | 2026-09-07 12:00 |  | Planning | Planned | 2
US-02 | 6 | Review persona variety across audiences | 2026-09-08 12:00 | 2026-09-08 12:00 |  | Planning | Planned | 2
US-02 | 7 | Prepare sample personas for discussion | 2026-09-09 12:00 | 2026-09-09 12:00 |  | Planning | Planned | 2
US-02 | 8 | Check generated profile structure | 2026-09-10 12:00 | 2026-09-10 12:00 |  | Planning | Planned | 2
US-02 | 9 | Review milestone 2 requirements | 2026-09-11 12:00 | 2026-09-11 12:00 |  | Planning | Planned | 2
SPRINT 4 BACKLOG — PLANNED
US-04 | 1 | Plan survey question input | 2026-09-15 12:00 | 2026-09-15 12:00 |  | Planning | Planned | 2
US-04 | 2 | Plan side-by-side persona responses | 2026-09-16 12:00 | 2026-09-16 12:00 |  | Planning | Planned | 2
US-04 | 3 | Define survey response structure | 2026-09-17 12:00 | 2026-09-17 12:00 |  | Planning | Planned | 2
US-04 | 4 | Review response behavior for different question types | 2026-09-18 12:00 | 2026-09-18 12:00 |  | Planning | Planned | 2
US-04 | 5 | Plan persona memory across interview turns | 2026-09-21 12:00 | 2026-09-21 12:00 |  | Planning | Planned | 2
US-04 | 6 | Define interview conversation flow | 2026-09-22 12:00 | 2026-09-22 12:00 |  | Planning | Planned | 2
US-04 | 7 | Plan insight themes and sentiment output | 2026-09-23 12:00 | 2026-09-23 12:00 |  | Planning | Planned | 2
US-04 | 8 | Plan product-use scoring by persona group | 2026-09-24 12:00 | 2026-09-24 12:00 |  | Planning | Planned | 2
US-04 | 9 | Review milestone 3 acceptance needs | 2026-09-25 12:00 | 2026-09-25 12:00 |  | Planning | Planned | 2
SPRINT 5 BACKLOG — PLANNED
US-05 | 1 | Review survey response consistency | 2026-09-28 12:00 | 2026-09-28 12:00 |  | Planning | Planned | 2
US-05 | 2 | Review interview persona consistency | 2026-09-29 12:00 | 2026-09-29 12:00 |  | Planning | Planned | 2
US-05 | 3 | Check planned scenarios across product categories | 2026-09-30 12:00 | 2026-09-30 12:00 |  | Planning | Planned | 2
US-05 | 4 | Plan theme and sentiment summaries | 2026-10-01 12:00 | 2026-10-01 12:00 |  | Planning | Planned | 2
US-05 | 5 | Plan agreement and behavior trend summaries | 2026-10-02 12:00 | 2026-10-02 12:00 |  | Planning | Planned | 2
US-05 | 6 | Define reasoning for persona-group scores | 2026-10-05 12:00 | 2026-10-05 12:00 |  | Planning | Planned | 2
US-05 | 7 | Sketch insights dashboard sections | 2026-10-06 12:00 | 2026-10-06 12:00 |  | Planning | Planned | 2
US-05 | 8 | Plan report content and order | 2026-10-07 12:00 | 2026-10-07 12:00 |  | Planning | Planned | 2
US-05 | 9 | Review report export requirements | 2026-10-08 12:00 | 2026-10-08 12:00 |  | Planning | Planned | 2
US-05 | 10 | Prepare milestone 4 work outline | 2026-10-09 12:00 | 2026-10-09 12:00 |  | Planning | Planned | 2
SPRINT 6 BACKLOG — PLANNED
US-08 | 1 | Plan dashboard theme and sentiment views | 2026-10-12 12:00 | 2026-10-12 12:00 |  | Planning | Planned | 2
US-08 | 2 | Plan key persona quote display | 2026-10-13 12:00 | 2026-10-13 12:00 |  | Planning | Planned | 2
US-08 | 3 | Plan validation score display | 2026-10-14 12:00 | 2026-10-14 12:00 |  | Planning | Planned | 2
US-08 | 4 | Plan PDF report sections | 2026-10-15 12:00 | 2026-10-15 12:00 |  | Planning | Planned | 2
US-08 | 5 | Prepare end-to-end test flow | 2026-10-16 12:00 | 2026-10-16 12:00 |  | Planning | Planned | 2
US-08 | 6 | Review open issues and next steps | 2026-10-19 12:00 | 2026-10-19 12:00 |  | Planning | Planned | 2
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | 31 Aug 2026 | Planned checkpoint after LLM foundation study | Discuss questions and confirm project direction
2 | 07 Sep 2026 | Milestone 1: prepare LLM concepts for Q&A | Review tokens, context, transformers, prompting and grounding
3 | 10 Sep 2026 | Planned Q&A checkpoint | Discuss milestone 1 topics and clarify open questions
4 | 15 Sep 2026 | Milestone 2: project scope and architecture | Review product, audience, persona model and experiment workflow
5 | 25 Sep 2026 | Planned milestone 3 review (workday before 26 Sep) | Review survey, interview and insight work
6 | 12 Oct 2026 | Milestone 4 work begins | Review dashboard, PDF report and end-to-end testing tasks

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 46237.5 | 46248.5 |  | Review planned sprint goal | Record any work that moved to the next sprint | Keep useful notes and clear task priorities | Suggested prompt for retrospective; team feedback not provided
2 | 2 | 46251.5 | 46262.5 |  | Review planned sprint goal | Record any work that moved to the next sprint | Keep useful notes and clear task priorities | Suggested prompt for retrospective; team feedback not provided
3 | 3 | 46265.5 | 46276.5 |  | Review planned sprint goal | Record any work that moved to the next sprint | Keep useful notes and clear task priorities | Suggested prompt for retrospective; team feedback not provided
4 | 4 | 46280.5 | 46290.5 |  | Review planned sprint goal | Record any work that moved to the next sprint | Keep useful notes and clear task priorities | Suggested prompt for retrospective; team feedback not provided
5 | 5 | 46293.5 | 46304.5 |  | Review planned sprint goal | Record any work that moved to the next sprint | Keep useful notes and clear task priorities | Suggested prompt for retrospective; team feedback not provided
6 | 6 | 46307.5 | 46314.5 |  | Review planned sprint goal | Record any work that moved to the next sprint | Keep useful notes and clear task priorities | Suggested prompt for retrospective; team feedback not provided
7